## Sheet1
Minutes of Meeting
Project Name: |  | RCM Ticketing Tool
Conducted On: |  | 2021-06-09
CMS Attendees: |  | Suman B , Dipak , Leena , Pushkal ,Ruchira ,Arvind
External Attendees : |  | Vrashab K
Sr. no. | Topics | Discussion / Changes asked | Next Action | Person Responsible | By When | Status
Date & Time
1 | USER MASTER | User will have multiple bank rights and he should have multiple bankwise, Querytype wise priority rights in user master. |  | Arvind |  | Open
2 | USER MASTER | Admin user should be able to change assigned user. he should able to see all tickets. |  | Arvind |  | Open
3 | Ticket MASTER | Batch wise grid for accept reject and duplicate of a ticket on ticket master |  | Arvind |  | Open
4 | Ticket MASTER | Show email attachments on ticket master. |  | Arvind |  | Open
5 | Ticket MASTER | Send email to location subject should be same as ticket subject. |  | Arvind |  | Open
6 | Ticket MASTER | Store email sent to location history. |  | Arvind |  | Open
7 | Ticket MASTER | if crn no changed, then rcm details should be fetched from RCM db. |  | Arvind |  | Open
8 | Ticket MASTER | Populate customer subtype,hierarchy code also from rcm db. |  | Arvind |  | Open
9 | Ticket MASTER | Provied search on email subject,batch number on ticket master dashboard. |  | Arvind |  | Open
10 | Ticket MASTER | Send email for duplicate and reject also on ticket master. |  | Arvind |  | Open
11 | Ticket Detials | Based on error types show NA in non important columnson Ticket Details page. |  | Arvind |  | Open
12 | Email Bot | Email bot should pickup bank from domain name |  | Vrashab |  | Open
12 | User priority logic | Logic to be planned basis matrix with customer query type and to set priority , no duplication entry to be allowed | Biz to share the validation matrix for existing 10-12 users | Dipak/leena |  | Open
13 | Email = batch ack status – ACCEPT REJECT , DUPLICATE | Business logic to be confirmed and shared with IT | Biz to have internal meet and to finalise | Suman |  | Open
14 | HANDLE - REPLY EMAIL , FWD EMAILS | Business logic to be confirmed and shared with IT | Biz to have internal meet and to finalise | Suman |  | Open
15 | RESPONSE TO CUSTOMER | Business logic to be confirmed and shared with IT | Biz to have internal meet and to finalise | Suman |  | Open